## Sheet1
Related User Story | Task Description | Initial Estimate | Assigned To | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3
Status Page - C | Full page. View creator, shirt name, and whether or not a business is accepting the request (and who that business is) | 6 | Trinidad | 4 | 2 | 0
Status Page - B | Full page. View creator, shirt name, and whether or not the creator has viewed the accepted request. |  | Nate | 2 | 1 | 0
Log In - B & C | Users can log in with an existing account clicking log-in button | 6 | Nate | 2 | 1 | 0
| Process validates whether or not account already exists via server info |  | Trinidad | 4 | 2 | 0
| Estimate Totals | 12 |  | 12 | 6 | 0